## Sheet1
Weekdag | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
Datum | time axis 2019-05-01 to 2020-01-24
Uitleg | 2019-05-13: Work; 2019-05-30: Hemelvaart; 2019-06-03: Bogota; 2019-06-17: Texas; 2019-06-24: Italie; 2019-07-15: work; 2019-08-12: Indonsie; 2019-09-09: work; 2019-10-11: Barcelona; 2019-10-21: work; 2019-11-07: work; 2019-12-06: Barcelona; 2019-12-25: Kerst
Projectdag | 2019-05-01: 1; 2019-05-02: 2; 2019-05-03: 3; 2019-05-06: 4; 2019-05-07: 5; 2019-05-08: 6; 2019-05-09: 7; 2019-05-10: 8; 2019-05-20: 9; 2019-05-21: 10; 2019-05-22: 11; 2019-05-23: 12; 2019-05-24: 13; 2019-05-27: 14; 2019-05-28: 15; 2019-05-29: 16; 2019-05-31: 17; 2019-06-20: 18; 2019-06-21: 19; 2019-07-01: 20; 2019-07-02: 21; 2019-07-03: 22; 2019-07-04: 23; 2019-07-05: 24; 2019-07-08: 25; 2019-07-09: 26; 2019-07-10: 27; 2019-07-11: 28; 2019-07-12: 29; 2019-07-22: 30; 2019-07-23: 31; 2019-07-24: 32; 2019-07-25: 33; 2019-07-26: 34; 2019-07-29: 35; 2019-07-30: 36; 2019-07-31: 37; 2019-08-01: 38; 2019-08-02: 39; 2019-08-05: 40; 2019-08-06: 41; 2019-08-07: 42; 2019-08-08: 43; 2019-08-09: 44; 2019-09-02: 45; 2019-09-03: 46; 2019-09-04: 47; 2019-09-05: 48; 2019-09-06: 49; 2019-09-16: 50; 2019-09-17: 51; 2019-09-18: 52; 2019-09-19: 53; 2019-09-20: 54; 2019-09-30: 55; 2019-10-01: 56; 2019-10-02: 57; 2019-10-03: 58; 2019-10-04: 59; 2019-10-07: 60; 2019-10-08: 61; 2019-10-09: 62; 2019-10-10: 63; 2019-10-14: 64; 2019-10-15: 65; 2019-10-16: 66; 2019-10-17: 67; 2019-10-18: 68; 2019-10-30: 69; 2019-10-31: 70; 2019-11-01: 71; 2019-11-04: 72; 2019-11-05: 73; 2019-11-06: 74; 2019-11-14: 75; 2019-11-15: 76; 2019-11-18: 77; 2019-11-19: 78; 2019-11-20: 79; 2019-11-21: 80; 2019-11-22: 81; 2019-11-25: 82; 2019-11-26: 83; 2019-11-27: 84; 2019-11-28: 85; 2019-11-29: 86; 2019-12-02: 87; 2019-12-03: 88; 2019-12-04: 89; 2019-12-05: 90; 2019-12-09: 91; 2019-12-10: 92; 2019-12-11: 93; 2019-12-12: 94; 2019-12-13: 95; 2019-12-16: 96; 2019-12-17: 97; 2019-12-18: 98; 2019-12-19: 99; 2019-12-20: 100; 2019-12-23: 101; 2019-12-24: 102; 2019-12-27: 103; 2019-12-30: 104; 2019-12-31: 105; 2020-01-02: 106; 2020-01-03: 107; 2020-01-06: 108; 2020-01-07: 109; 2020-01-08: 110; 2020-01-09: 111; 2020-01-10: 112; 2020-01-13: 113; 2020-01-14: 114; 2020-01-15: 115; 2020-01-16: 116; 2020-01-17: 117; 2020-01-20: 118; 2020-01-21: 119; 2020-01-22: 120; 2020-01-23: 121; 2020-01-24: 122
Task
Writing Project Brief | bar: 2019-05-01; 2019-05-03; 2019-05-10; 2019-05-13
Analysis of existing concepts | bar: 2019-05-01 to 2019-05-03; 2019-05-06 to 2019-05-07
Literature review on EE | bar: 2019-05-06 to 2019-05-10
Kick-off Meeting | bar: 2019-05-13
Prepare Main Research | bar: 2019-05-20 to 2019-05-24
Execute Main Research | bar: 2019-05-27 to 2019-05-29; 2019-07-01 to 2019-07-04
Write Academic Paper | bar: 2019-07-04 to 2019-07-05; 2019-07-08
Field Research Target Group | bar: 2019-05-31; 2019-07-08 to 2019-07-12
Market analysis | bar: 2019-06-20 to 2019-06-21
Create Design recommendations | bar: 2019-07-22 to 2019-07-26
Midterm Evaluation Meeting | bar: 2019-07-29
Adjust to feedback | bar: 2019-07-30 to 2019-08-01
Design campaign elements | bar: 2019-08-01 to 2019-08-02; 2019-08-05 to 2019-08-08; 2019-10-17 to 2019-10-18; 2019-10-30 to 2019-11-01; 2019-11-04 to 2019-11-05
Literature review on implementation strategy | bar: 2019-08-08 to 2019-08-09
Create business model canvas (and apply other methods) | bar: 2019-09-02 to 2019-09-06
Formulation of brand identity | bar: 2019-09-16 to 2019-09-17
Develop Marketing Strategy (4P's, etc.) | bar: 2019-09-17 to 2019-09-20
(Co-)Design of Marketing expressions | bar: 2019-09-30 to 2019-10-04
Create Implementation strategy | bar: 2019-10-07 to 2019-10-10; 2019-10-14 to 2019-10-16; 2019-11-04 to 2019-11-05
Create Roadmap | bar: 2019-11-06; 2019-11-14 to 2019-11-15; 2019-11-18 to 2019-11-21
Green Light Meeting | bar: 2019-11-25
Adjust to feedback | bar: 2019-11-22; 2019-11-25 to 2019-11-28
Create final presentation | bar: 2019-11-27 to 2019-11-29; 2019-12-02 to 2019-12-05; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-18
Finish thesis report (lay-out, visualisation, etc.) | bar: 2019-11-29; 2019-12-02 to 2019-12-05; 2019-12-09 to 2019-12-13; 2019-12-16 to 2019-12-18
Graduation Ceremony | bar: 2019-12-19